## feature list
Workflows | ID | Security Domain | Feature | Description | Applies To | Priority | Status | Dependencies | Owner | Notes
1 – Device Manufacturing | DEV-001 | Device Security | Immutable Device ID | Assign every device a globally unique immutable identifier during manufacturing. | Smart Glasses, BWC | Critical | Planned | Manufacturing System | Firmware | Cannot be modified after production
1 – Device Manufacturing | IDN-001 | Identity | Device Certificate | Provision each device with a unique X.509 certificate. | Smart Glasses, BWC | Critical | Planned | PKI | Firmware | Device identity for mTLS
1 – Device Manufacturing | DEV-002 | Device Security | Secure Boot | Prevent execution of unauthorized firmware during boot. | Smart Glasses, BWC | Critical | Planned | Bootloader | Firmware | Root of Trust
1 – Device Manufacturing | DEV-003 | Device Security | Firmware Signing | Digitally sign firmware images before deployment. | Smart Glasses, BWC | Critical | Planned | PKI | Firmware | Prevent malicious firmware
1 – Device Manufacturing | DEV-004 | Device Security | Anti-Rollback Protection | Prevent installation of older vulnerable firmware versions. | Smart Glasses, BWC | High | Planned | Secure Boot | Firmware | Store firmware version securely
1 – Device Manufacturing | DEV-005 | Device Security | Secure Element Support | Store certificates and cryptographic keys in secure hardware. | Smart Glasses, BWC | High | Planned | TPM / Secure Element | Hardware | Preferred over software storage
2 – Device Provisioning | ADM-001 | Administration | Officer Assignment | Associate officer identity with assigned devices. | Backend | Critical | Planned | IAM | Backend | Maintain assignment history
2 – Device Provisioning | ADM-002 | Administration | Device Assignment | Bind Body Camera, Glasses and Mobile Device to an officer. | Backend | Critical | Planned | Device Registry | Backend | Support multiple devices
2 – Device Provisioning | IDN-002 | Identity | Certificate Installation | Install operational certificates during provisioning. | All Devices | Critical | Planned | PKI | Firmware | Separate manufacturing and operational certificates
2 – Device Provisioning | COM-001 | Communications | Secure Device Pairing | Securely pair wearable devices with authorized mobile device. | BWC, Glasses, Mobile | Critical | Planned | Certificates | Mobile | Use mutual authentication
2 – Device Provisioning | AUTH-001 | Authentication | Mutual Authentication | Devices authenticate each other before communication. | All Devices | Critical | Planned | Certificates | Firmware | No anonymous devices
2 – Device Provisioning | AUTHZ-001 | Authorization | Device Authorization | Verify device assignment before allowing synchronization. | Backend, Mobile | Critical | Planned | Device Registry | Backend | Reject unauthorized pairings
2 – Device Provisioning | LOG-001 | Audit | Provisioning Audit Log | Record every provisioning activity. | Backend | High | Planned | Audit Service | Backend | Supports forensic investigations
3 – Recording | EVD-001 | Evidence Protection | Secure Recording Session | Start authenticated recording session. | BWC, Glasses | Critical | Planned | Authentication | Firmware | Record officer identity
3 – Recording | CRY-001 | Cryptography | Video Encryption | Encrypt recordings immediately during capture. | BWC, Glasses | Critical | Planned | AES-256 | Firmware | No plaintext storage
3 – Recording | EVD-002 | Evidence Protection | Metadata Generation | Attach timestamp, GPS, Device ID, Officer ID and case metadata. | BWC, Glasses | Critical | Planned | GPS | Firmware | Metadata protected
3 – Recording | EVD-003 | Evidence Protection | Evidence Hashing | Generate SHA-256 hash after recording completion. | BWC, Glasses | Critical | Planned | Crypto Library | Firmware | Original evidence hash
3 – Recording | EVD-004 | Evidence Protection | Digital Signature | Digitally sign completed recording. | BWC, Glasses | Critical | Planned | PKI | Firmware | Non-repudiation
3 – Recording | CRY-002 | Cryptography | Secure Local Storage | Store recordings only in encrypted storage. | BWC, Glasses | Critical | Planned | Secure Storage | Firmware | Prevent offline extraction
3 – Recording | LOG-002 | Audit | Recording Audit Trail | Log recording start, stop and events. | BWC, Backend | High | Planned | Audit Service | Firmware | Tamper resistant logs
4 – Synchronization | COM-002 | Communications | Secure Wi-Fi Connection | Establish encrypted communication channel. | BWC, Glasses, Mobile | Critical | Planned | WPA3 | Mobile | Prefer WPA3 Enterprise
4 – Synchronization | AUTH-002 | Authentication | Device Authentication | Authenticate both endpoints before synchronization. | All Devices | Critical | Planned | Certificates | Mobile | mTLS
4 – Synchronization | AUTHZ-002 | Authorization | Synchronization Authorization | Verify synchronization permissions. | Mobile | Critical | Planned | IAM | Mobile | Assignment validation
4 – Synchronization | COM-003 | Communications | Encrypted File Transfer | Encrypt evidence during transfer. | Mobile, BWC, Glasses | Critical | Planned | TLS | Mobile | End-to-end encryption
4 – Synchronization | EVD-005 | Evidence Protection | Transfer Hash Verification | Verify integrity after synchronization. | Mobile | Critical | Planned | SHA-256 | Mobile | Compare source and destination hashes
4 – Synchronization | EVD-006 | Evidence Protection | Transfer Verification Report | Generate transfer verification status. | Mobile | High | Planned | Audit | Mobile | Success / Failure
4 – Synchronization | EVD-007 | Evidence Protection | Secure Local Deletion | Securely erase evidence after successful verification (policy controlled). | BWC, Glasses | High | Planned | Hash Verification | Firmware | Optional retention policy
5 – Evidence Upload | AUTH-003 | Authentication | Mobile Authentication | Authenticate mobile application to backend. | Mobile | Critical | Planned | OAuth / Certificates | Mobile | MFA for officers if applicable
5 – Evidence Upload | COM-004 | Communications | Secure TLS Upload | Upload evidence through encrypted channel. | Mobile, Cloud | Critical | Planned | TLS 1.3 | Mobile | Certificate validation
5 – Evidence Upload | CLD-001 | Cloud Security | Secure Evidence Upload | Validate uploaded evidence before acceptance. | Cloud | Critical | Planned | API Gateway | Backend | Reject invalid uploads
5 – Evidence Upload | EVD-008 | Evidence Protection | Cloud Hash Verification | Verify uploaded evidence integrity against original hash. | Cloud | Critical | Planned | SHA-256 | Backend | Integrity validation
5 – Evidence Upload | EVD-009 | Evidence Protection | Cloud Digital Signature | Apply server-side evidence signature. | Cloud | High | Planned | PKI | Backend | Additional integrity assurance
5 – Evidence Upload | CLD-002 | Cloud Security | Evidence Vault Storage | Store validated evidence in immutable secure storage. | Cloud | Critical | Planned | Secure Storage | Backend | WORM/immutable storage preferred
5 – Evidence Upload | LOG-003 | Audit | Upload Audit Trail | Record upload, verification and storage events. | Backend | High | Planned | Audit Service | Backend | Chain of custody

## pending workflows
Pending Workflows
Officer Authentication & Session Management (Login, MFA, Session Tokens, Logout)
Live Streaming & Real-Time Communications (Glasses/BWC → Mobile → Cloud)
AI Processing Pipeline (Inference, Summarization, Face/Object Detection, AI Audit Logs)
Evidence Access & Review (Search, Playback, Export, Sharing, RBAC)
OTA Firmware & Application Updates (Secure updates, signature verification, rollback protection)
Device Loss / Theft / Remote Lock & Wipe (Compromised device response)
Administration & Device Lifecycle Management (Enrollment, Reassignment, Retirement)
Evidence Retention, Archive & Secure Deletion (Legal hold, retention policies, cryptographic erasure)
Incident Response & Forensic Investigation (Tamper detection, alerts, forensic data collection)
Device Decommissioning (Certificate revocation, key destruction, secure wipe)

## scratch pad
PKI Infrastructure
Boot up | PKI{decrypt[AES 256 Key]} | {decrypt} | AES 256
Data in Use | UnEncrypted
Data in Motion | Encrypted
Date in Rest | Encrypted
Video file creation on the body cam\ | Hash is Computed (SHA256) & Stored in body cam
Video File Transfer / Sync to mobile device | Hash is Computed in transit and stored in mobile device
Video File copied to dest. (mobile Device) | Hash is computed at the Dest.